## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Team Member 1 | 2026-09-03 | Nested exception cause extraction failed in Java stack trace parser. | Sprint 1 | Backend Developer | Logical | Added recursive exception unwrapping for nested 'Caused by' exception clauses in regex parser. | 2026-09-03 | Closed | Retested successfully with multi-cause Java logs.
2 | Team Member 2 | 2026-09-04 | Multipart log file upload crashed on files exceeding 5MB. | Sprint 1 | Backend Developer | Functional | Implemented chunked streaming reader with 10MB limit and content-length validation. | 2026-09-04 | Closed | 8MB crash logs uploaded and parsed successfully.
3 | Team Member 3 | 2026-09-05 | ChromaDB HNSW cosine query returned NaN for empty sanitized trace strings. | Sprint 1 | AI/ML Developer | Logical | Added empty input guard returning zero-vector fallback before invoking sentence-transformers embedding. | 2026-09-05 | Closed | Empty input handled gracefully without crashing.
4 | Team Member 4 | 2026-09-06 | Dark mode glassmorphism dashboard had poor text contrast on secondary metrics. | Sprint 1 | Frontend Developer | User Interface | Updated Tailwind dark theme color tokens to slate-300 and added glass-panel border highlights for WCAG AA compliance. | 2026-09-06 | Closed | Visual contrast verified across all resolutions.
5 | Team Member 1 | 2026-09-07 | Triage agent assigned Medium severity to fatal OutOfMemoryError crashes. | Sprint 2 | AI/ML Developer | Logical | Increased triage heuristic weighting for OOM, HeapSpace, and SIGSEGV exceptions to Critical. | 2026-09-08 | Closed | Benchmark accuracy improved to 96.25%.
6 | Team Member 2 | 2026-09-08 | C/C++ GDB regex failed to parse hexadecimal address offset notation. | Sprint 2 | Backend Developer | Standards | Updated regex pattern to support 0x... in <func>+0x.. GDB syntax and frame extraction. | 2026-09-09 | Closed | GDB core dumps parsed with 100% extraction precision.
7 | Team Member 3 | 2026-09-09 | LangGraph pipeline stalled when log analyzer received syslog format without frames. | Sprint 2 | Backend Developer | Maintainability | Added default empty frame dictionary to maintain state transition contract across all agent nodes. | 2026-09-10 | Closed | Pipeline resilience verified against unstructured syslogs.
8 | Team Member 4 | 2026-09-11 | Duplicate detection agent flagged unrelated timeouts due to common logger prefix. | Sprint 3 | AI/ML Developer | Logical | Differentiated Chunk 2 error trace embeddings from generic Chunk 1 titles, prioritizing trace tokens. | 2026-09-12 | Closed | Duplicate detection precision reached 80.0%.
9 | Team Member 1 | 2026-09-12 | Root cause agent produced ungrounded hypotheses when vector matches were weak. | Sprint 3 | AI/ML Developer | Logical | Added speculative guarding flag (is_speculative=True) and advisory warning when confidence < 0.70. | 2026-09-13 | Closed | Hallucinations eliminated on partial logs.
10 | Team Member 2 | 2026-09-13 | Unified git diff patch contained invalid hunk headers for single-line fixes. | Sprint 3 | AI/ML Developer | Standards | Standardized unified diff hunk header generation (@@ -start,len +start,len @@) to follow git diff syntax. | 2026-09-14 | Closed | Patch applies cleanly via git apply without syntax errors.
11 | Team Member 3 | 2026-09-14 | Glassmorphism code block overflowed horizontally on long unified diff patch lines. | Sprint 3 | Frontend Developer | User Interface | Added overflow-x-auto and custom horizontal scrollbar styling to diff container in DiagnosisView. | 2026-09-14 | Closed | Code block scrolls cleanly on mobile and desktop.
12 | Team Member 4 | 2026-09-16 | ChromaDB 3-chunk re-indexing failed when bug title contained special Unicode characters. | Sprint 4 | Backend Developer | Logical | Sanitized document IDs and stripped non-ASCII characters from vector metadata dictionaries. | 2026-09-17 | Closed | Knowledge base growth feedback loop validated.
13 | Team Member 1 | 2026-09-17 | Defect pattern analytics divided by zero on empty database initialization. | Sprint 4 | Backend Developer | Logical | Added zero-division guard defaulting component risk score to 0.0 when total bug count is zero. | 2026-09-18 | Closed | Empty database state handles cleanly without 500 error.
14 | Team Member 2 | 2026-09-18 | Demonstration preset button did not clear prior diagnosis state before loading. | Sprint 4 | Frontend Developer | User Interface | Added state reset dispatch prior to loading new preset defect data into active diagnostic viewer. | 2026-09-19 | Closed | Preset switching works instantaneously without state bleed.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others